Stakeholder Engagement Plan - Clermont

| Objectives | Strategies | Target audience | Timeframe | Communication/media | Evaluation measures |
| --- | --- | --- | --- | --- | --- |
| - Establish awareness of the place-based planning project | - Identification of health-related stakeholders (local, regional, visiting, referral) - Identification of other key local stakeholder groups - Provide general project information using multiple modes - Discuss with key stakeholders | - Key local and regional health service members - Community leaders and groups - General community | June 2022 Ongoing | - Email stakeholders with introductory project information - Follow-up phone calls with stakeholders - Targeted face-to-face visits with key individuals and community leaders - Discuss with existing group (if relevant) or establish new reference group - Meetings with relevant regional health service execs and managers | - Number of planning meetings held, and number and diversity of attendees - Community communications delivered |
| - Increase awareness of the place-based planning project - Engage stakeholders to successfully conduct participatory co-design process | - Recruit well-connected Project Support Officer (PSO) - Recruit and engage appropriate range of local and regional stakeholders for reference group - Identify and engage all stakeholders - Follow place-based planning process | - Key local and regional health service members - Community leaders and groups - General community | July -Oct 2022 | - Advertise PSO position in local newsletter, facebook groups and noticeboards - Regular meetings between JCU research team and local PSO (zoom and F2F) - Participation in local reference group meetings by PSO and JCU (F2F/email/zoom) - Advertise workshops through reference group network, flyers in newsletters and social media posts - Explore appropriate local options for workshops and interviews (structures and locations etc) | - Number and methods of communications delivered - Number of planning meetings, workshops and interviews held, and diversity of attendees - Development of action plan |
| - Implementation and monitoring of priority actions from place-based plan | - Group prioritisation of actions in plan - Pilot implementation led by PSO and reference group - Provide ongoing feedback to key stakeholders and broader community | - Key local and regional health service members - Community leaders and groups - General community | Oct 2022-March 2024 | - Regular meetings between JCU research team and local PSO (zoom and F2F) - Participation in local reference group meetings by PSO and JCU (F2F/email/zoom) - Updates to key stakeholders and the community via flyers, newsletters and on social media | - Attendance at reference group meetings - Delivery of priority actions - Number and methods of communications delivered |
| - Evaluation of process, impacts and outcomes - Share learnings with the local community and broader project stakeholders | - Conduct evaluation of co-design process - Evaluate impacts and outcomes of actions - Provide feedback to key stakeholders and local community - Share learnings with broader project stakeholders | - Key local and regional health service members - Community leaders and groups - General community | Oct 2022-March 2024 | - Participation in local reference group meetings by PSO and JCU (F2F/email/zoom) - Updates to key stakeholders and the community via flyers, newsletters and on social media - Newsletters and meetings with Project Technical Reference Group, TAAHC Board and Clinical Leadership Group | - Number and diversity of participants in evaluation activities - Number of newsletters, posts feedback sessions - Interviews with participants |
| - Support sustainability of actions and further development | - Develop strategic plan for future development (supported with data and evidence) - Standing item on reference group agenda | - Key local and regional health service members - Community leaders and groups - General community | March 2024 and beyond | - Regular discussions between stakeholders at reference group meetings beyond the project - Updates to key stakeholders and the community via flyers, newsletters and on social media | - Development of strategic plan (or continuation of the action plan) - Agenda item |

# Site specific stakeholders: Clermont

| Organisation | Name | Position/Role | Onsite/Visit frequency | Email | Phone | Address when in town | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Health Services |  |  |  |  |  |  |  |
| Clermont MPHS |  | DON | Onsite |  |  | 26 Francis Street |  |
| Clermont MPHS |  | NUM | Onsite |  |  | 26 Francis Street |  |
| Clermont Country Practice |  | Doctor/Practice owner | Onsite |  |  | 38 Jellicoe Street |  |
| Clermont Country Practice |  | Practice manager | Onsite |  |  | 38 Jellicoe Street |  |
| Clermont Pharmacy |  | Pharmacist | Onsite |  |  | 48 Daintree Street |  |
| Clermont Dental Services |  | Dentists | Visit 3 days per week |  |  | Turners Arcade, Capella Street |  |
| QAS |  |  | Onsite |  |  |  |  |
| Stream Services (aka Clermont Country Care) |  | Founder and Director | Onsite |  |  | 2 Daintree Street |  |
| Stream Services (aka Clermont Country Care) |  | Project Worker | Onsite |  |  |  |  |
| Bodyfix Physiotherapy (Funded) |  | Physiotherapist | Onsite or Visiting? |  |  |  |  |
| Central Highlands Optical |  | Optometrist | Fortnightly |  |  | 41 Capella Street |  |
| Central Queensland Rural Health (Funded by NQPHN) |  | Midwife – antenatal, postnatal, lactation services. | Fortnightly |  |  |  |  |
| Clarity Hearing Solutions |  |  | Regularly |  |  | 41 Capella Street |  |
| Compleat Nutrition (Synergy Health Centre; Funded) |  |  | Monthly |  |  |  |  |
| Construct Health |  | Physiotherapy | Fortnightly |  |  |  |  |
| Feros Care |  | Local Area Coordinator |  |  |  |  |  |
| Flying Skin Cancer Doctor |  |  | 3 monthly |  |  |  |  |
| Harris Chiropractic Spine Clinic |  |  | Monthly |  |  |  |  |
| Hinterland Community Care |  | Aged Care Service Coordinator |  |  |  |  |  |
| Hinterland Community Care |  | General Manager |  |  |  |  |  |
| Isaac Navicare |  | Mental Health Care Navigator |  |  |  |  |  |
| Lifestyle Therapies and Training Solutions |  |  |  |  |  |  |  |
| Northern Australia Primary Health Ltd |  | Diabetes educator Exercise physiology and dietician | Bi-monthly ?Telehealth |  |  |  |  |
| RFDS Dental Service |  | Dentist Dental assistant | Visited 10-19 May 2022 |  |  |  |  |
| RFDS |  |  |  |  |  |  |  |
| The Marshman Family Trust (Pioneer Podiatry; Funded) |  | Podiatrist | Fortnightly |  |  |  |  |
| Towers Podiatry (Funded) |  | Podiatrist |  |  |  |  |  |
| True Relationships and Reproductive Health (Funded) |  | General Practitioner Registered Nurse | Appears to be 3 monthly Telehealth |  |  | Clermont MPHS |  |
| Clermont Community Housing and Other Services Inc. |  | Vice President | Onsite: Mon/Tues/Thurs/Fri 12.30-3pm Weds 12.30-2pm |  |  | 2 Lime Street |  |
| Belyando Enterprise Network Inc (BENI) |  |  |  |  |  |  |  |
| CHANT |  | Local Reference Group | Onsite |  |  |  |  |
| Clermont4Doctors |  |  | Onsite |  |  |  |  |
| Clermont and District Senior Citizens Association |  |  |  |  |  |  |  |
| Clermont Meals on Wheels |  |  |  |  |  |  |  |
| CRU – Community Resource Unit Ltd |  |  |  |  |  |  |  |
| Isolated Children’s Parents’ Association |  | President Secretary Treasurer Branch Mentor | Onsite |  |  |  |  |
| Men’s Shed |  |  | Onsite |  |  | 25 Power House Lane |  |
| Clermont CWA |  |  |  |  |  | CWA Hall, 28 Sirius Street |  |
| Rotary Clermont |  | President Secretary Treasurer | Onsite |  |  |  |  |
| Greater Whitsunday Communities |  | Senior Coordinator |  |  |  |  |  |
| Isaac Shire |  | Mayor |  |  |  |  |  |
| Isaac Regional Council |  | Chief Executive |  |  |  |  |  |
| Isaac Regional Council |  | Head of Advocacy and External Affairs – Office of the Mayor/CEO |  |  |  |  |  |
| Isaac Regional Council |  | Coordinator Executive Support Office of the Mayor and CEO |  |  |  |  |  |
| JCU |  | Isaac Shire Project Team |  |  |  |  |  |
| MHHS |  | CEO |  |  |  |  |  |
| MHHS |  | Executive Director Research and Innovation |  |  |  |  |  |
| MHHS |  | Executive Director – Public Health & Rural Services |  |  |  |  |  |
| MHHS |  | Director, Strategy and Planning |  |  |  |  |  |
| MHHS |  | Senior Director, Strategy, Governance and Engagement |  |  |  |  |  |
| NQPHN |  | Integration and Partnerships Specialist - Mackay |  |  |  |  |  |